## Slide 1: SOLUTION-1 Upgrading BPM 8.5.6 to BAW 19.0.0.1

## Slide 2
Solution-1:
  S1-A: Upgrading BPM 8.5.6 to BAW 19.0.0.1.
  S1-B: Migrating Oracle 11G to Oracle 12C R2.

## Slide 3: Steps for Migrating ORACLE 11G to ORACLE 12C R2

## Slide 4: Oracle Database Migration:
We are using Oracle 11g for IBM BPM 8.5.6, So BAW 19.0.0.1 doesn't support Oracle 11G. We need to use Oracle 12C R2(Release 2 .i.e. Oracle 12.2.0.1).

## Slide 5
Step-1:
Install Oracle 12C R2 on the target system.
Step-2:
Export all the data from source Oracle 11G.
Step-3:
Import entire data to Oracle 12C R2.
Step-4:
Unplug Oracle 11G from the BPM 8.5.6
Step-5:
Plug In Oracle 12G to BPM 8.5.6.

## Slide 6: Steps for Upgrading BPM 8.5.6 to BAW 19.0.0.1

## Slide 7
  As BAW 19.0.0.1 supports ORACLE 12c R2 and we have migrated ORACLE 11G to 12C R2. Now we can upgrade our source BPM 8.5.6 to target BAW 19.0.0.1 without any issues.

## Slide 8
Step-1:
Check your WAS Version if it's <8.5.5.15 then apply WAS FIXPACK 8.5.5.15. i.e. BAW 18.0.0.1 requires 8.5.5.15.
When we apply this fixpack 8.5.5.15, the JDK 1.8. is installed automatically
Step-2:
Now apply BAW 18.0.0.1 FIXPACK to BPM 8.5.6.
Step-3:
Now you need to apply BAW 19.0.0.1 refresh pack.
Step-4:
BAW 18.0.0.1/19.0.0.1 requires 3 more users to support case management and other functions so we need to create below three additional users.
a) ICNUSER.
b) DOSUSER.
c) TOSUSER.

## Slide 9
Step-5:
Validate the Database and upgrade database.
Step-6:
Enable JDK 1.8 to deployment manager and all the nodes and then synchronize.
Make sure JAVA SDK 1.8 is enabled for DMGR and all nodes.
Step-7:
Start deployment manager and all other nodes.

## Slide 10: Possible Pros and Cons :

## Slide 11
Pros:
Takes less time as we are upgrading BPM 8.5.6 to BAW 19.0.0.1 instead of migrating.
Migrating needs exporting and importing of each and every artifact form source system to target system, so it's time consuming and error prone.
More productive and less downtime.
Old instances are also migrated in this process, so we need not maintain source system until current active instances are completed/Finished.

## Slide 12
Cons:
The database upgradation may fail for some reasons.
The BPM profile may crash during profile upgradation.
BAW 19.0.0.1 may not support a few feature of BPM 8.5.6

## Slide 13
Workarounds for the concerns:
The database upgradation may fail for some reasons, so we need to take extra care during database migration and it's recommended to take backups.
The BPM profile may crash during profile upgradation, so we need to take profile backups as well.
BAW 19.0.0.1 may not support a few feature of BPM 8.5.6, so we need to identify each of them and provide an alternative.

## Slide 14: Pre- requisites :
  Oracle 12C R2 (12.2.0.1).
JAVA SDK 1.8.
WAS 8.5.5.15 FIXPACK.
BAW 18.0.0.1 FIXPACK.
BAW 19.0.0.1 REFERSHPACK

## Slide 15: Project Plan:
The project plan includes below environments.
a) Sandbox
b) SIT.
c) UAT.
d) PRODUCTION.

## Slide 16: SANDBOX Plan:
Here we need to replicate the production environment with all the 30+ applications.
Need to migrate and test all the applications in BAW 19.0.0.1, once migration is done.
It's a critical stage and setting up this environment takes time. 90 days to replicate the production system and upgrading it to BAW 19.0.0.1.
Initial BPM 8.5.6 setup with all 30 applications: 30 Days
Database up-gradation & BAW up-gradation : 15 days for 6 administration resources.

## Slide 17
Understanding existing functionality of all applications : 30 days for 30 to 40 applications for 10 development resources.
Identifying removed components and providing alternative solutions and re-implementing application if needed: 60 days for 10 development resources for 30 applications.
Testing all applications and providing bug fixes, if any: 30 to 45 days for 10 testing and development resources.

## Slide 18: SIT Plan:
Setting SIT environment by the admin team : 10 Days(This setup is done parallel when the development team is implementing their solution)
Moving applications and resources from SANDBOX to SIT : 10 days (This is also done parallel when the development team is implementing their solution)
Testing all application and fixing any testing and development team : 30 days.

## Slide 19: UAT Plan:
Setting UAT environment by the admin team : 10 Days(This setup is done in parallel when the development team is implementing their solution)
Moving applications and resources from SIT to UAT : 10 days (This is also done in parallel when the development team is implementing their solution)
Testing all application and fixing bugs by testing and development team respectively: 30 days.

## Slide 20: Production Plan:
Setting up parallel production environment and moving applications and resources to production : 5 to 10 days.

## Slide 21
Timelines :
The entire solution, that includes Sandbox development to Production deployment, takes : Min 180 days.
Resource Table:
TEAM | MEMBERS
Development Team | 10 Members
Administration Team | 6 Members
Testing Team | 10 Members
Architect/Consultant | 1 Members
Project Manager | 1 Member

## Slide 22: Application Migration or Code Migration:

## Slide 23
The newly Upgraded BAW 19.0.0.1 supports some new feature for better performance and some of the features from source BPM 8.5.6 are also deprecated/removed.
So we need to identify all new feature that are supported by target system and the features that are deprecated/removed in target system.
Created a separated document "BPM Up -gradation from 8.5.6 to BAW 18.0.0.1.doc" for alternative approaches for deprecated/removed features/components, so you can refer "BPM Up-gradation from 8.5.6 to BAW 18.0.0.1.doc".