## Slide 1: Solution 2 Installing Fresh BAW 19.0.0.1

## Slide 2
S2-A: Installing Fresh BAW 19.0.0.1.
S2-B: Re-configuring resources, that were created in source WAS, in target WAS.
S2-C: Deploying dependency modules and other artifact in target WAS environment.
S2-D: Installing Fresh Oracle 12C R2.
S2-E: Migrating data from Oracle 11G to Oracle 12C R2 database.

## Slide 3: Installing Fresh BAW 19.0.0.1
High-Level Steps for Setting up database for BAW 19.0.0.1(Created a separate low-level document for installation process) :
Oracle Database :
BAW 19.0.0.1 supports ORACLE 12C R2 or 18C.
Step-1:
Install Oracle 12C R2

## Slide 4: High-Level Steps for Installing BAW 19.0.0.1(Created a separate low-level document for installation process):
As BAW 19.0.0.1 supports ORACLE 12c R2 or 18c. So we can Installed 12C R2 or 18C then we can install BAW 19.0.0.1 without any issues.
In order to install BAW 19.0.0.1, first we need to install BAW 18.0.0.1 and need to apply BAD 19.0.0.1 refresh pack

## Slide 5
Step-1:
Download 18.0.0.1 software packages and install them. Here WAS 8.5.5.13 and JAVA JDK 1.8 come with BAW 18.0.0.1 by default
Step-2:
Apply WAS 8.5.5.15 refresh pack as BAW 19.0.0.1 needs WAS 8.5.5.15
Step-3:
Apply BAW 19.0.0.1 Cumulative FIXPACK to get BAW 19.0.0.1
Step-4:
Create Database users, BPM 8.5.6 or 8.5.7 or 8.6 requires only three(PDWUSER,CMNUSER and BPMUSER) users. But for BAW 19.0.0.1 needs three more users
a) ICNUSER. d)BPMUSER
b) DOSUSER. e)CMNUSER
c) TOSUSER. f)PDWUSER

## Slide 6
Step-5:
Create Process Center(PC) or Process Server(PS) environment.
Step-7:
Start deployment manager and all other nodes and servers.

## Slide 7: Possible Pros and Cons.:
Pros:
Need not to export and import data from source database to target database, So it's easy to setup compared to Solution-1.
As we are installing fresh environment, we need not to worry about WAS profiles crash during up-gradation, so it's less error prone compared to Solution-1
More productive and less downtime. Means when we follow Solution-1 we need to shutdown all profiles and database in order to take their backup consequently it leads to production downtime.

## Slide 8
Cons:
Live instances will not be available in target system.
All resources like JDBC data sources..etc that are configured in old WAS need to be re-configured in target WAS environment.
All the enterprise and web modules that are deployed on old WAS need to be re-deployed on target system.
Need to deploy all process applications in the target system which is time consuming and error prone.
Need to re-create some process applications.
Migrating needs exporting and importing of each and every artifact form source system to target system, so it's time consuming and error prone.

## Slide 9: Workarounds for the concerns:
We need to maintain two production systems, one for old instances and other for new instances as live instances are not available in the target system.

## Slide 10: Pre-requisites:
Oracle 12C R2(12.2.0.1).
JAVA SDK 1.8.
BAW 18.0.0.1 Software Packages(1,2,3).
WAS 8.5.5.15 FIXPACK.
BAW 19.0.0.1 REFERSHPACK

## Slide 11: Project Plan:
The project plan includes below environments.
a) Sandbox
b) SIT.
c) UAT.
d) PRODUCTION.

## Slide 12: SANDBOX:
Here we need to replicate the production environment with all the 30+ applications.
Need to re-configure the resources, that were configured in source WAS environment, in target WAS environment.
Need to re-deploy the dependent modules, that were deployed on source WAS environment, on target WAS environment.
Need to migrate and test all the applications in BAW 19.0.0.1, once migration is done.
Initial BPM 8.5.6 setup with all 30 applications: 30 Days for 6 administration resources.
Install separate BAW 19.0.0.1 and Oracle 12c R2 : 5 days for 6 administration resources.
Re-Configure old resources and re-deploy all dependent modules in new WAS environment: 30 days.
Understanding existing functionality of all applications : 30 days for 30 to 40 applications for 10 development resources.

## Slide 13
Identifying removed components and providing alternative solutions and re-implementing application if needed: 60 days for 10 development resources for 30 applications.
Testing all applications and providing bug fixes, if any: 30 to 45 days for 10 testing and development resources.

## Slide 14: SIT:
Setting SIT environment by the admin team : 20 Days(10 days for re-configuring old resources and old dependent modules on production environment)
Moving applications and resources from SANDBOX to SIT : 10 days (This is also done in parallel when the development team is implementing their solution)
Testing all application and fixing any testing and development team : 30 days.

## Slide 15: UAT:
Setting UAT environment by the admin team : 20 Days(10 days for re-configuring old resources and old dependent modules on production environment)
Moving applications and resources from SIT to UAT : 10 days (This is also done in paralle when the development team is implementing their solution)
Testing all application and fixing bugs by testing and development team respectively: 30 days.

## Slide 16: Production:
Setting up parallel production environment and moving applications and resources to production : 5 to 10 days.
Re-configuring old resources and re-deploying dependent modules on parallel target production environment : 20 Days

## Slide 17
Timelines :
The entire solution, that includes Sandbox development to Production deployment, takes : Min 210 days.
Resource Table:
TEAM | MEMBERS
Development Team | 10 Members
Administration Team | 6 Members
Testing Team | 10 Members
Architect/Consultant | 1 Members
Project Manager | 1 Member

## Slide 18: Application Migration or Code Migration:
The newly Upgraded BAW 19.0.0.1 supports some new feature for better performance and some of the features from source BPM 8.5.6 are also deprecated/removed.
So we need to identify all new feature that are supported by target system and the features that are deprecated/removed in target system.
Created a separated document "BPM Up-gradation from 8.5.6 to BAW 18.0.0.1.doc" for alternative approaches for deprecated/removed features/components, so you can refer "BPM Up-gradation from 8.5.6 to BAW 18.0.0.1.doc".