## Slide 1: Solution-3: (S3-C + Solution-1)

## Slide 2
Upgrading BPM 8.5.6 to BAW 19.0.0.1 and code enhancement for better performance

## Slide 3
S3-A: Upgrading BPM 8.5.6 to BAW 19.0.0.1.
S3-B: Migrating Oracle 11G to Oracle 12C R2.
S3-C: Identifying component or services that need code changes for better performance.

## Slide 4
Steps for Migrating ORACLE 11G to ORACLE 12C R2 :
Same as Solution-1
Steps for Upgrading BPM 8.5.6 to BAW 19.0.0.1
Same as Solution-1

## Slide 5: Possible Pros and Cons.:
Pros:
Same pros as mentioned in Solution-1.
And better performance as we'll enhance existing code as per new features.
Cons:
Same cons as mentioned in Solution-1.

## Slide 6: Workarounds for the concerns:
The database up-gradation may fail for some reasons, so we need to take extra care during database migration and it's recommended to take backups.
The BPM profile may crash during profile up-gradation, so we need to take profile backups as well.
BAW 19.0.0.1 may not support a few feature of BPM 8.5.6, so we need to identify each of them and provide an alternative.

## Slide 7: Pre- requisites :
Oracle 12C R2(12.2.0.1).
JAVA SDK 1.8.
WAS 8.5.5.15 FIXPACK.
BAW 18.0.0.1 FIXPACK.
BAW 19.0.0.1 REFERSHPACK

## Slide 8: Project Plan:
The project plan includes below environments.
  a)Sandbox.
  b) SIT.
  c) UAT.
  d) PROUCTION.

## Slide 9
SANDBOX:
Sandbox plan as in Solution-1
Code enhancement for better performance : 30 Days.
SIT:
Setting SIT environment by the admin team : 10 Days(This setup is done parallel when the development team is implementing their solution)
Moving applications and resources from SANDBOX to SIT : 10 days (This is also done parallel when the development team is implementing their solution)
Testing all application and fixing any testing and development team : 30 days.

## Slide 10
UAT:
Setting UAT environment by the admin team : 10 Days(This setup is done parallel when the development team is implementing their solution)
Moving applications and resources from SIT to UAT : 10 days (This is also done parallel when the development team is implementing their solution)
Testing all application and fixing bugs by testing and development team respectively: 30 days.

## Slide 11
Production:
Setting up parallel production environment and moving applications and resources to production : 5 to 10 days.

## Slide 12: Time lines :
The entire solution, that includes Sandbox development to Production deployment, takes : Min 210 days.
Resource Table:
TEAM | MEMBERS
Development Team | 10 Members.
Administration Team | 6 Members.
Testing Team | 10 Members.
Architect/Consultant | 1 Member.
Project Manager | 1 Member.

## Slide 13: Application Migration or Code Migration:
The newly Upgraded BAW 19.0.0.1 supports some new feature for better performance and some of the features from source BPM 8.5.6 are also deprecated/removed.
So we need to indentify all new feature that are supported by target system and the features that are deprecated/removed in target system.
Created a separated document "BPM Up-gradation from 8.5.6 to BAW 18.0.0.1.doc" for alternative approaches for deprecated/removed features/components, so you can refer "BPM Up-gradation from 8.5.6 to BAW 18.0.0.1.doc".