## Slide 1: Solution-4:(S4-F + Solution-2)

## Slide 2
Installing Fresh BAW 19.0.0.1 and code enhancement for better performance

## Slide 3
S4-A: Installing Fresh BAW 19.0.0.1.
S4-B: Re-configuring resources, that were created in source WAS, in target WAS.
S4-C: Deploying dependency modules and other artifact in target WAS environment.
S4-D: Installing Fresh Oracle 12C R2.
S4-E: Migrating data from Oracle 11G to Oracle 12C R2 database.
S4-F: Identifying component or services that need code changes for better performance.

## Slide 4
High-Level Steps for Setting up database for BAW 19.0.0.1
Oracle Database :
BAW 19.0.0.1 supports ORACLE 12C R2 or 18C.
Step-1:
Install Oracle 12C R2.

## Slide 5: High-Level Steps for Installing BAW 19.0.0.1(Created a separate low-level document for installation process):
As BAW 19.0.0.1 supports ORACLE 12c R2 or 18c. So we can Installed 12C R2 or 18C then we can install BAW 19.0.0.1 without any issues.
In order to install BAW 19.0.0.1, first we need to install BAW 18.0.0.1 and need to apply BAW 19.0.0.1 refresh pack

## Slide 6
Step-1:
Download 18.0.0.1 software packages and install them. Here WAS 8.5.5.13 and JAVA JDK 1.8 come with BAW 18.0.0.1 by default
Step-2:
Apply WAS 8.5.5.15 refresh pack as BAW 19.0.0.1 needs WAS 8.5.5.15
Step-3:
Apply BAW 19.0.0.1 Cumulative FIXPACK to get BAW 19.0.0.1

## Slide 7
Step-4:
Create Database users, BPM 8.5.6 or 8.5.7 or 8.6 requires only three(PDWUSER,CMNUSER and BPMUSER) users. But for BAW 19.0.0.1 needs three more users
  a)ICNUSER.
  b)DOSUSER.
  c)TOSUSER.
  d)BPMUSER.
  e)CMNUSER.
  f) PDWUSER.
Step-5:
Create Process Center(PC) or Process Server(PS) environment.
Step-6:
    Start deployment manager and all other nodes and servers.

## Slide 8: Possible Pros and Cons:
Pros:
Same pros as mentioned in Solution-2.
And better performance as we'll enhance existing code as per new features.
Cons:
Same cons as mentioned in Solution-2.

## Slide 9: Workarounds for the concerns
We need to maintain two production systems, one for old instances and other for new instances as live instances are not available in the target system.

## Slide 10: Pre- requisites :
Oracle 12C R2(12.2.0.1).
JAVA SDK 1.8.
BAW 18.0.0.1 Software Packages(1,2,3).
WAS 8.5.5.15 FIXPACK.
BAW 19.0.0.1 REFERSHPACK

## Slide 11: Project Plan:
The project plan includes below environments.
  a)Sandbox.
  b) SIT.
  c) UAT.
  d) PRODUCTION.

## Slide 12
SANDBOX:
Sandbox plan as in Solution-1
Code enhancement for better performance : 30 Days.
SIT:
Setting SIT environment by the admin team : 20 Days(10 days for re-configuring old resources and old dependent modules on production environment)
Moving applications and resources from SANDBOX to SIT : 10 days (This is also done parallel when the development team is implementing their solution)
Testing all application and fixing any testing and development team : 30 days.

## Slide 13
UAT:
Setting UAT environment by the admin team : 20 Days(10 days for re-configuring old resources and old dependent modules on production environment)
Moving applications and resources from SIT to UAT : 10 days (This is also done parallel when the development team is implementing their solution)
Testing all application and fixing bugs by testing and development team respectively: 30 days.

## Slide 14
Production:
Setting up parallel production environment and moving applications and resources to production : 5 to 10 days.
Re-configuring old resources and re-deploying dependent modules on parallel target production environment : 20 Days

## Slide 15: Time lines :
The entire solution, that includes Sandbox development to Production deployment, takes : Min 240 days.
Resource Table:
TEAM | MEMBERS
Development Team | 10 Members.
Administration Team | 6 Members.
Testing Team | 10 Members.
Architect/Consultant | 1 Member.
Project Manager | 1 Member.

## Slide 16
Application Migration or Code Migration:
The newly Upgraded BAW 19.0.0.1 supports some new feature for better performance and some of the features from source BPM 8.5.6 are also deprecated/removed.
So we need to indentify all new feature that are supported by target system and the features that are deprecated/removed in target system.
Created a separated document "BPM Up-gradation from 8.5.6 to BAW 18.0.0.1.doc" for alternative approaches for deprecated/removed features/components, so you can refer "BPM Up-gradation from 8.5.6 to BAW 18.0.0.1.doc".