## IBM BPM 8.6 Upgrade Preparation
Questions | Component | Environment(Source/Target) | Comments | Notes
What is the IBM BPM version of the environment? | BPM | Source | If your source BPM Versin is 8.5 or more then you can directly apply fixpack to upgradte it to 8.6 otherwise you need to migrate the environment and applications.
What is the Operating System (OS) and its version of the source environment? | BPM | Source | Make sure that the source OS is supported by IBM BPM 8.6. IBM BPM V8.6.0 or later requires Java Runtime Environment (JRE) 8. If your system does not support Java 8, you must either upgrade your operating system to a newer version that supports Java 8, or migrate to IBM BPM V8.5.7 CF2017.06, which is the last version that provides 32-bit Java 7 in the remote migration utility.
Does the source environment have more than one deployment environments? | WAS | Source | Only one deployment environment can be migrated at a time.
Is the source environment a stand alone server or a ND server? | WAS | Source | ND server
If the source environment is a ND server, is it setup as single cluster or 3 cluster? | WAS | Source | Three Cluster
If the source environment is a multiple cluster setup, how many nodes are used? | WAS | Source | Single Node
Does the source environment have a Web Server? If yes, what type? How many nodes? | BPM | Source | Yes WebServer is there on one Node
Does the source environment have a Load Balancer? If yes, please share its details and architecure diagram of the source environments with LB and Web Servers | BPM | Source | BPM configuration runs over the Websphere Application Server. We can integrate any type of web server like IHS, Tomcat etc..
What is the source environment BPM database type and version? DB2/Oracle/SQL Server | DB | Source | IBM DB2 v10.5.0.6
Does the database jdbc connection use integrated security or OS auth or Kerberos in the source environments? | DB | Source | integrated security
Does the source environment use any other languages or locales | BPM | Source | No
Identify the 3rd party JAR or LIBs or modified jar files deployed on the source environment. Example: local_policy.jar or sm_cryptoj.jar | WAS/BPM | Source | Yes
What are the applications which consumes data from the source BPM environment? Also Identity the data elements used. | BPM | Source | Applications developed on the platform like Java, ESB, ODM etc.. consumes the data from the source BPM. So we need to list out all these data source applications
Are there any special custom integrations used to serve the data to the other applications? | BPM | Source | REST and SOAP services are available for integrations to serve the data to the other applications. So we need to list out REST AND SOAP services here
What are the application which provides data to the source BPM Environments? | BPM | Source | Applications developed on the platform like Java, ESB, ODM etc.. consumes the data from the source BPM. So we need to list out all these data source applications
Are there any ETL jobs which transfer data from/to source BPM environments? | BPM | Source | Mediation flows are the one which can support the data transformation between source and destination in source BPM.
The following default users are removed from IBM BPM. Make sure the application is not tightly coupled with these exact users • bpmadmin • bpmAuthor • tw_admin • tw_author • tw_portal_admin • tw_runtime_server • tw_user • tw_webservice | BPM | Source | If your applications are using users that have been removed, you must assign the required security roles to them again after migration.
The following default authentication aliases are removed from IBM BPM. Make sure the application is not tightly coupled with these exact aliases. • Bspace_Auth_Alias • WPSDB_Auth_Alias • WPSDB_Auth_Alias_XAR • SCA_Auth_Alias • BPC_Auth_Alias • BPMPrimaryAdmin_Auth_Alias • BPMAdmin_Auth_Alias • BPMAuthor_Auth_Alias • BPMUser_Auth_Alias • BPMWebservice_Auth_Alias • RALSecurity_Auth_Alias • processdblogon • processdblogon_XAR • performancedblogon • performancedblogon_XAR • PROCSVR_Auth_Alias • PERFDW_Auth_Alias | BPM | Source | If your applications are using aliases that have been removed, you must re- create them manually in the target environment after migration.
Does the source environments have saved searches in Process Portal? If so, document all of them. | Process Portal | Source | Make sure that none of them have conditions with an empty value. Otherwise, you will see only a blank page in Process Portal and will have to re-create those saved searches.
Does the source environment have 100Custom configurations? If yes, please document them. | BPM | Source | Yes. The location of 100Custom XML configuration files and the system files that contain the default values is dependent on the server type that you are configuring. It is also dependent on whether your environment is a stand-alone environment or a clustered network deployment environment.
Are there any changes made to the Process Admin Console security access thru console.xml? | BPM | Source | No
Document the artifact count grouped by artifacts type in the source Process Center | Process Center | Source
Document the number of instances grouped by its status in the source environment which we are planning to migrate | BPM | Source
Document the number of documents which needs to be migrated from pre 8.5 document attachment functionality. Do a count on document attachment table to get this number. | BPM | Source
Do you have stand-alone tasks in your source environment? | BPM | Source | Stand-alone tasks are no longer supported in IBM Business Process Manager V8.5.0 and later versions. If you migrated from Teamworks and still have stand-alone tasks in your source environment, you will not be able to use them in V8.6.0. You must use an alternative approach to achieve the functionality that was provided by the stand-alone task.
Does the source environment use LDAP/AD? | WAS | Source | AD
Does the source environment use SSO? If yes, what type? | WAS | Source | No
Are there any special logout functionality in the source environments based on SSO/SLO? | WAS | Source | No
Are there other WebSphere Application on the same DE in the source environment? | WAS | Source | No
Check and document custom JMS configurations | WAS | Source | Yes
Check and document custom Schedulers | WAS | Source | No
Check and document custom Environment variables | WAS | Source | No
Check and document custom Shared library configurations | WAS | Source | No
Check and document custom Work Manager | WAS | Source
Ensure no errors on old environment startup - Dmgr - Collect logs. Document and Resolve issues (if any). | Dmgr | Source | Yes
Ensure no errors on old environment startup - Node Agent - Collect logs. Document and Resolve issues (if any). | Node Agent | Source | Yes
Ensure no errors on old environment startup - Profiles - Collect logs. Document and Resolve issues (if any). | Profile/DE | Source | Yes
Do you use any special OS service accounts user to run the BPM in source environment? | WAS | Source | No
Check if some pre-migration maintenance/cleanup can be peformed? | BPM | Source
Completed process instances | BPM | Source | Before you begin the migration procedure, verify that your target migration environment is supported and that your source migration environment is ready to be migrated
Completed tasks | BPM | Source
Inactive process application snapshots | BPM | Source
Prune Performance Data Warehouse data | BPM | Source
Durable subscription messages | BPM | Source
Are you planning to do a in-place upgrade/migration? | BPM | Target | Upgrade
Evaluate Detailed System Requirements. Ensure that your system meets all system requirements. | BPM | Target | Yes
What is the Operating System (OS) and its version of the target environment?
Check if the OS of the target environment is supported by IBM. |  |  | OracleLinux7
Is the DataBase Server shared or Dedicated? | DB Server | Target | Yes
Check if the database type and version are supported by the IBM BPM product | DB Server | Target | Dedicated
If it is SQL Server database make sure MSDTC and XA transactions are enabled on the database. | DB Server | Target | Yes
Check Memory required for App Server | BPM | Target | No
Check Memory required for DB Server | DB Server | Target | Yes
Check DB Server and App Server are in same time zone and sync'ed with same time server | App/DB Server | Target | Yes
Identify Drive for the install. Usually D: | BPM | Target | Yes
Check Disk Space on the installation drive. Minimum 100GB. | BPM | Target
Install Chrome Browser in new Server | App Server | Target | Yes
Install 7 zip (http://www.7-zip.org/a/7z1604-x64.exe) | App Server | Target | Yes
Install BareTail (https://www.baremetalsoft.com/baretail/download.php?p=m) | App Server | Target | Yes
Make sure you have a well documented infrastructure architecture diagram of source and destination environment | BPM | Both
Do you have test data to test the migration? If yes, request your QA team to identify and record the test results in the source environments. If not request your QA team to create new test data in the source environment before the migration. | BPM | Source | You can keep your source environment running and do the migration testing in parallel using the cloned databases, as long as you make sure that your test environment is isolated from the production environment. Make sure that the two environments do not use the same Process Center. After you finish testing migration, configure a new deployment environment that you intend to use as the target production environment. You can clone the latest version of the production database to keep the database data up-to-date, or you can switch your new target deployment environment to point to the source production database when you run the migration